## Trang tính1
TASK TITLE | TASK OWNER | START DATE | DUE DATE | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Tet | [6 empty] | Tet | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9
|  |  |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | END
|  |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
Sprint 1 (Project Initiating) |  | 2026-01-05 | 2026-01-10
Prepare and analysis project needs, project scope | All member | 2026-01-05 | 2026-01-05 | bar: Mon; Sat to Sun
Report 1 (Project Introduction) | DucHT | 2026-01-06 | 2026-01-06 | bar: Tue; Sat to Sun
Development Plan | All member | 2025-01-06 | 2025-01-07 | bar: Tue to Wed; Sat to Sun
Project Schedule | All member | 2025-01-07 | 2025-01-07 | bar: Wed; Sat to Sun
Project Management | All member | 2025-01-07 | 2025-01-08 | bar: Wed to Thu; Sat to Sun
Report 2 (Project Plan) | All member | 2025-01-08 | 2025-01-10 | bar: Thu to Sat; Sat to Sun
Sprint 2 (Project General Initialization) |  | 2026-01-11 | 2026-01-25
Document | bar: Mon to Fri
Database Design | All member | 2026-01-11 | 2026-01-14 | bar: Sun to Wed
Usecase | All member | 2026-01-14 | 2026-01-15 | bar: Wed to Thu
Project Architeture Design | All member | 2026-01-15 | 2026-01-18 | bar: Thu to Sun
Functional Requirment | All member | 2026-01-18 | 2026-01-20 | bar: Sun to Tue
Report 3 (Software Requirment Specification) | All member | 2026-01-20 | 2026-01-22 | bar: Tue to Thu
Report 4 (Software Design) | All member | 2026-01-22 | 2026-01-25 | bar: Thu to Sun
Coding |  | 2026-01-26 | 2026-02-02
Initialize Back-end Project | AnDB | 2026-01-26 | 2026-01-26 | bar: Mon
Back-end Project Common | HieuCH, DucHT, AnDB | 2026-01-27 | 2026-01-30 | bar: Tue to Fri
Initialize Front-end Project | DucHT | 2026-01-26 | 2026-01-26 | bar: Mon
Front-end Project Common | HieuCh, DangTM | 2026-01-27 | 2026-02-02 | bar: Tue to Mon
Sprint 3 (Project Development) |  | 2026-02-03 | 2026-02-08
Document |  | 2026-02-03 | 2026-02-08 | bar: Tue to Sun
Test Case | All member | 2026-02-03 | 2026-02-05 | bar: Tue to Thu
Sequence Diagram | All member | 2026-02-05 | 2026-02-08 | bar: Thu to Sun
Coding |  | 2026-02-08 | 2026-03-10
API | All member | 2026-02-08 | 2026-03-10 | bar: Sun; Mon to Tue
Unit Test API | All member | 2026-03-04 | 2026-03-10 | bar: Wed to Tue
Screen | All member | 2026-02-10 | 2026-03-10 | bar: Mon to Tue
Testing |  | 2026-03-10 | 2026-03-15
List Test Case | DucHT | 2026-03-10 | 2026-03-11 | bar: Tue to Wed
Verify Test Project FMS | All member | 2026-03-11 | 2026-03-12 | bar: Wed to Thu
Fix Bug Project FMS | All member | 2026-03-12 | 2026-03-15 | bar: Thu to Sun
Sprint 4 (Project Finishing) |  | 2026-03-10 | 2026-03-15
Document |  | 2026-03-10 | 2026-03-13 | bar: Tue to Fri
Test Case | All member | 2026-03-13 | 2026-03-15 | bar: Fri to Sun
Testing |  | 2026-03-10 | 2026-03-15
List Test Case | DangTM | 2026-03-10 | 2026-03-13 | bar: Tue to Fri
Verify Test Project FMS | All member | 2026-03-13 | 2026-03-15 | bar: Fri to Sun